## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a player I want to view a help screen so that I can know how to play the game. | 1) Create a rectangle object to act as the background for help screen 2) Create button on the bottom of the pause menu screen 3) Add a text body explaining the game 4) Create a disable help screen button | 4, 5 | Make a very simple UI representation of a help screen | Functional | 1 | 1 | Caleb Thurston - 100%
12 | As a player I want to be able to overcome obstacles so that I can continue to progress. | 1) Make a simple design plan for the level, using shapes to map out future obstacle/platform sprites 2) Add obstacle and platform sprites 3) Make obstacle and platform sprites interactable 4) Add special interactions with different sprites as needed | 3, 4, 5 | Make walls in the design plan interactable | Functional | 3 | 2.5 | Caleb Thurston - 75%, Mariia Maksymenko – 20%, Kieran Firkin – 5%
2 | As a player I want to be able to pause the game so that I can stop the game while I go do something else. | 1) Create a canvas object in unity 2) Add a panel component and upload image to the panel 3) Create a button component and add it to the canvas 4) Tie the function "isActive" to the button component | 4,5 | Make a very simple UI representation of a pause menu | Functional | 1 | 1 | Caleb Thurston - 100%
13 | As a player I want to be able to overcome traps so that I can continue to progress. | 1) Create prefabricated trap game objects in unity 2) Attach Collider2D components said objects 3) Attach a script to said objects which kills the player on collision | 5 | Make a simple implementation of traps | Functional | 4 | 4 | Mariia Maksymenko – 70%, Kieran Firkin – 30%