## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
3 | As a player I want to be able to see my progress in the level so that I can see how much of the level I have left. | 1) Implement a way to track player's locations 2) Implement a "finish line" point in both players' directions 3) Implement a way to track players' progress from the start location to finish location 4) Implement aforementioned as a UI element | 3 | Make a UI representation of players' level progress | Functional | 2 | 2 | Arius Ahmad - 90%, Kieran Firkin - 7%, Caleb Thurston - 3%
8 | As a player I want to be able to wall jump so that I can traverse when no platforms are available. | 1) Implement wall sliding so players have time to make a jump 2) Implement a "is colliding with wall" check 3) Implement a wall jumping function 4) Implement an animation flip based on the jump direction | 3 | Implement wall sliding and colliding check | Functional | 2 | 0.5 | Mariia Maksymenko - 100%
12 | As a player I want to be able to overcome obstacles so that I can continue to progress. | 1) Make a simple design plan for the level, using shapes to map out future obstacle/platform sprites 2) Add obstacle and platform sprites 3) Make obstacle and platform sprites interactable 4) Add special interactions with different sprites as needed | 3 | Make a simple design plan for the level | Functional | 3 | 1 | Caleb Thurston - 100%