## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a player I want to view a help screen so that I can know how to play the game. | 4,5 | High | In Progress | 1
2 | As a player I want to be able to pause the game so that I can stop the game while I go do something else. | 4,5 | Med | In Progress | 1
3 | As a player I want to be able to see my progress in the level so that I can see how much of the level I have left. | 3 | Low | Completed | 2
4 | As a player I want to be able to play with my friends so that we can have fun together. | 2 | High | Completed | 2
5 | As a player I want to be able to progress to a new stage/level so that I can get closer to the end goal. | 5 | Low | Not Started | 4
6 | As a player I want to be able to reach an end goal so that I can win the game. | 4 | High | Completed | 2
7 | As a player I want to be able to tell the difference between my character and the character of player 2 so that I know which character I am controlling. | 1,2,3,4 | High | Completed | 4
8 | As a player I want to be able to wall jump so that I can traverse when no platforms are available. | 3,4 | Med | Completed | 2
9 | As a player I want to move the character around so that I can explore the level. | 1,2,3 | High | Completed | 2
10 | As a player I want to be able to sabotage the other player so that I can impede their progress. | 5 | Med | Not Started | 3
11 | As a player I want to be able to overcome traps so that I can continue to progress. | 5 | Med | Not Started | 4
12 | As a player I want to be able to overcome obstacles so that I can continue to progress. | 3,4,5 | Med | In Progress | 3
13 | As a player I want to be able to grapple so that I can progress through the level faster. | 5 | Low | Not Started | 2
14 | As a player I want to be able to collect power-ups so that I can avoid traps more easily. | 5 | Low | Not Started | 3
15 | As a player I want to change sound settings so that I can avoid blowing my ears out. | 5 | Med | Not Started | 2
16 | As a player I want to have a countdown before the beginning of a round so that I can know when to start. | 5 | Low | Not Started | 1