## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a player I want to view a help screen so that I can know how to play the game. | 1) Create a rectangle object to act as the background for help screen 2) Create button on the bottom of the pause menu screen 3) Add a text body explaining the game 4) Create a disable help screen button | 4, 5 | Make a very simple UI representation of a help screen | Functional | 1 | 0.7 | Caleb Thurston - 100%
8 | As a player I want to be able to wall jump so that I can traverse when no platforms are available. | 1) Implement wall sliding so players have time to make a jump 2) Implement a "is colliding with wall" check 3) Implement a wall jumping function 4) Implement an animation flip based on the jump direction | 3, 4 | Fix all the bugs in the previous implementation of wall jumping | Functional | 2 | 2 | Mariia Maksymenko - 100%
12 | As a player I want to be able to overcome obstacles so that I can continue to progress. | 1) Make a simple design plan for the level, using shapes to map out future obstacle/platform sprites 2) Add obstacle and platform sprites 3) Make obstacle and platform sprites interactable 4) Add special interactions with different sprites as needed | 3, 4, 5 | Make walls in the design plan interactable | Functional | 3 | 1.5 | Caleb Thurston - 95%, Mariia Maksymenko - 5%
2 | As a player I want to be able to pause the game so that I can stop the game while I go do something else. | 1) Create a canvas object in unity 2) Add a panel component and upload image to the panel 3) Create a button component and add it to the canvas 4) Tie the function "isActive" to the button component | 4,5 | Make a very simple UI representation of a pause menu | Functional | 1 | 0.5 | Caleb Thurston - 100%
6 | As a player I want to be able to reach an end goal so that I can win the game. | 1) Establish where the end of the level would be for both players 2) Make two objects in Unity representing finish lines 3) Create a visual (UI) representation of finish lines for each player 4) Make Unity display a message when a player wins | 4 | Implement a fully functioning finish line for both players | Functional | 2 | 2 | Arius Ahmad - 100%