## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
7 | As a player I want to be able to tell the difference between my character and the character of player 2 so that I know which character I am controlling. | 1) Implement at least two different character models for each player. 2) Implement player models idle and movement animations 3) Assign different movement types to different players | 1 (continued in 2) | Assign different movement types to different players (WASD for player 1 and <- -> for player 2) | Functional | 4 | 3.5 | Mariia M. 100%
9 | As a player I want to move the character around so that I can explore the level. | 1) Implement funtionality to move around screen using "WASD" or arrow keys. 2) Implement a jump functionality to allow mid-air movement 3) Implement the ability to change the trajectory that the players fall at 4) Add a check if the players are grounded | 1 (continued in 2) | Make sure both characters have the ability to jump | Functional | 2 | 2 | Mariia M. 60%, Kieran Firkin 40%
4 | As a player I want to be able to play with my friends so that we can have fun together. | 1) Implement a camera for each player 2) Make the cameras follow each player 3) Implement a split screen divider | 2 | Implement a split screen + cameras | Functional | 2 | 2 | Caleb Thurston 50%, Kieran Firkin 50%